## Slide 1: Software Project Management (SPM)
Lecture 6
Activities & Time Planning
Dr. Daniel Keret

## Slide 2: Reading Assignment
Software Project Management, Bob Hughes and Mike Cotterell, McGraw-Hill, 3rd Edition.
Chapter 6
A Guide to the Project Management Body of Knowledge, PMI Publications, 3rd Edition, 2004
Chapter 6

## Slide 3: Activities & Time Planning
Breakdown WBS to Activities and Tasks
Activities Sequencing
Activity Resource Estimating
Activity Duration Estimation.
Scheduling of Work
  Network Analysis of Scheduling
  CPM & Interdependencies Charts (Critical Path, Fast Tracking & Crashing)
Schedule Control

## Slide 4: Breakdown WBS to Activities and Tasks
Activity – Element of Work Perform During the Course of a Project. It has:
  Expected Duration
  Expected Cost
  Expected Resource Requirement
  Activities Can be Further Divided Into Tasks
  Task: A Task Effort Is What A Professional Employee Should Know and is NOT Detailed in the Work Plan
The Activities Milestones are Derived from the WBS
Examples: Define Interface Requirement, Design Interfaces, Create Test Data

## Slide 5: Defining an Activity
Break a WBS Task to a Smaller (time, effort, resource wise) Controllable Activities.
Use Templates of Activities From Previous Projects and Adopt Professional Organizations (ISO, IEEE) Templates
Rolling Wave: Activity that is Planned For Execution in the Near Term Should be Very Detailed. Others can be Kept in an High level Form.
Use Expert Judgment
Planning Component: When there is not enough data to generate WBS Item, an higher level WBS can be a basis for high level project schedule.
Each Activity is Assigned with the Resources it Needs in order to be Completed (Time, Cost, manpower, etc.)

## Slide 6: Activity Resource Estimating
Identify needed Resourced (Manpower, Equipment, H/W, Etc)
Identify Quantity of Each Resource
Verify Resource Availability to Perform The Activity
Resource Breakdown Structure (RBS)
  Hierarchical Structure by Resource Category and Type ( Programmer, Analyst. Employee, Contractor)
Techniques Used for Estimation
  Expert Judgment
  Published Estimating Data
  Project Management Software ( For Resource Breakdown Structure, Resource Availability and Resource Rates Purposes)

## Slide 7: Activities Duration Estimation
The Duration Estimation Is a Progressive Task. The More Accurate the Activity is Defined a Better Estimate is Evaluated.
Techniques Used For Estimation
  Expert Judgment
  Analogous Estimation (Similar Activity, Historical Information)
  Parametric Estimation (Function Point, Etc)
  Three Point Estimation: Most Likely, Optimistic, Pessimistic ( Average of the 3 can be a good baseline)
  Reserve (Contingency, Risk, Etc)
Duration Estimation Example:
  2 Weeks +/- 2 days (8-12 Days)
  15% probability of Exceeding 3 Weeks

## Slide 8: Activities Sequencing
Identify and Document the Logical Relationships among Scheduled Activities.
The Activities Will Be Sequenced According to:
  Precedence Relationships
  Leads To Support Later Development
  Project Schedules and Milestones
Based on:
  Project Scope Statement
  Activity List
  Milestone List
  Approved Change Requests

## Slide 9: Precedence Diagram Method
Activities Are Nodes (AON – Activities On Node)
4 Types of Precedence Relationships (Arrows)
  Finish To Start
  Finish To Finish
  Start To Start
  Start To Finish
Dependency Determination
  Mandatory (Hard Logic)
  Discretionary (Preferred Logic, Best Practice)
  External Dependency (Project – Non Project Relationship, Legal Constrains, Supplies Delivery Deadlines, Etc)
Loops are NOT Allowed
Dangles (Dead Ends) Are NOT Allowed
Lagged Activities are shown on the arrows ( Documentation starts 2 days after Test Start Dates)
Hammock Activity – Has Zero Time. Represents Resources such as Overheads with Constant Cost Over the Duration of a Set of Activities

## Slide 10: Test Plan

## Slide 11: Activity Labeling Convention For Sequencing Purposes
Activity Label
Activity Description
Earliest Start
Earliest Finish
Latest Start
Latest Finish
Activity Span (Duration Between Earliest Start and Latest Finish – Maximum Time Allowed)
Float (Duration Between Earliest Start and Latest Start. Zero Span Indicates Critical Activity. Any Delay Will Impact the Finish Date Of the Project)

## Slide 12: Critical Path Method - CPM
The Forward Pass – Identify the Earliest Date an Activity Can Start
The Backward Pass – The Latest Date an Activity Can Start Without Delaying The End Date Of The Project.
The Critical Pass – Calculate the Float Time. The Critical Pass are the Activities with Zero Float Time.
  The Activities on the Critical Path should be paid a special Attention as Any Delay in these activities will Postpone The Project Completion Date
  Any wish to Shorten the Project Schedule Should Deal With The Critical Path Activities

## Slide 13
3

## Slide 14
3

## Slide 15
0
0
3

## Slide 16: Schedule Compression
Crashing – Analyzing Schedule Compression with MINIMAL Cost Increase
Fast Tracking – Activities Which are Schedule to Perform in Sequence (Discretionary) will Perform in Parallel, This Will Add RISK to the Project

## Slide 17: Apply Calendars
Project Calendar: ASSIGN ACTUAL DATES TO THE PROJECT SCHEDULE
  Adjust Holidays and others “Vacation Days”
Resources Calendar
  Non Availability of Resources On Certain Dates
  Trainings Dates,
  Working Hours Information (Part Time Employee)
Resource Leveling
  Shared or Critical resources May be Limited or not Available in Certain Time.
  The Project Management May Wish to Keep Some Resources at a Reasonable Stable Level.
  These Will Require Adjustments to the Project Schedule
Generate Project Schedule Baseline for approval and tracking of the actual performance

## Slide 18: Schedule Control
Reports the Current status of the project schedule
Detects the factors that create schedule change
Determine that the project schedule has changed
Manages the actual change as it occurs

## Slide 19: Schedule Control Tools and Techniques
Progress Report – Current Schedule Status
  Actual start and finish dates
  Remaining duration for unfinished schedule activities
Schedule change control system
  Paperwork, tracking system and approval levels for the schedule change procedure
Performance Measurements
  Schedule Performance Index (SPI), Schedule Variance (SV)
  Project Management Software
  Variance Analysis: Compare Target schedule dates with actual/forecast ones. Used for deviation detection and correction activities (Example: A major delay in non critical path activity may have a small impact)
  Schedule comparison bar chart

## Slide 20: Schedule Control Outputs
Schedule Model Updates
  Modifications to the project schedule model
  Notification of appropriate changes to the stakeholders
  New project schedule network diagram is developed
Schedule Baseline Update ( As a result of approved change requests)
Performance measurements
Requested changes
Recommended corrective actions
Lessons learned documentation – updates
Updates of relevant project’s sub planes